## PH-Phases
Phase ID | Phase Name | Summary | Goals | Objectives
PH-01 | Full Conversion (Decision-Centric Core) | Deliver the core decision engine for contract-first ordering, pricing enforcement, and rule-driven fulfillment to replace spreadsheets and tribal knowledge. | Enforce contracts and pricing at order time; Execute compliant fulfillment without manual interpretation | Orders are created with correct pricing and terms on first pass; Manual contract validation is eliminated for standard orders; Pricing, approval, and substitution decisions are fully auditable
PH-02 | Automation (Operational Scale) | Automate exception handling, approvals, and multi-source fulfillment to increase throughput and reduce operational firefighting. | Reduce operational escalations and manual intervention; Increase order throughput without additional headcount | Majority of orders process without manual escalation; Automated approvals handle most margin and compliance thresholds; Fulfillment routing executes consistently across warehouses
PH-03 | Scale (Predictability & Expansion) | Extend the OMS to support new warehouses, vendors, regulations, and analytics with confidence and predictable financial outcomes. | Enable rapid expansion without increasing compliance or margin risk; Improve forecasting accuracy and financial predictability | New warehouses and vendors onboard with minimal configuration effort; Demand, margin, and service-level forecasting is reliable; Audit readiness is achieved without manual reconciliation

## DEL-Deliverables
Deliverable ID | Strategy Ref | Blueprint Ref | Phase Ref ID | Requirement Type | Deliverable Name | Deliverable Description | Notes | Complexity | Effort | Hours | Epic Roll-Up | ELI Roll-Up
DEL-001 | CAP-001 | BP-1765865704672 | PH-01 | Experience | Contract Management | Manage customer profiles, contracts, service terms, and compliance requirements so orders are evaluated against the correct agreements and constraints. |  | Medium | 8 | 120 | 3 | 9
DEL-002 | CAP-002 | BP-1765865704672 | PH-01 | Experience | Inventory Management | Provide real-time visibility and control over inventory across warehouses and vendor sources to support accurate sourcing, allocation, and fulfillment decisions. |  | Medium | 8 | 120 | 3 | 9
DEL-003 | CAP-003 | BP-1765865704672 | PH-01 | Experience | Order Management | Create, validate, and manage sales orders with contract-first pricing and controlled lifecycle changes enforced at order time. |  | High | 13 | 160 | 4 | 12
DEL-004 | CAP-004 | BP-1765865704672 | PH-01 | Experience | Fulfillment Orchestration | Orchestrate compliant, rule-driven fulfillment across warehouses and vendors by applying rules for splits, substitutions, and service levels. |  | High | 13 | 160 | 3 | 9
DEL-005 | CAP-005 | BP-1765865704672 | PH-01 | Experience | Purchase Management | Coordinate purchasing from vendors based on demand, inventory gaps, and contract terms to ensure supply decisions align with pricing, compliance, and margin goals. |  | Medium | 8 | 100 | 3 | 9
DEL-006 | CAP-006 | BP-1765865704672 | PH-01 | Workflow | Sales Order Processing | Create, validate, price, and route sales orders through approvals to a “ready for fulfillment” state with full auditability. |  | High | 13 | 140 | 1 | 5
DEL-007 | CAP-007 | BP-1765865704672 | PH-01 | Workflow | Fulfillment Execution | Route fulfillment, allocate inventory, generate pick/pack/ship instructions, and confirm shipment with auditability. |  | High | 13 | 100 | 1 | 5
DEL-008 | CAP-008 | BP-1765865704672 | PH-01 | Workflow | Purchase Replenishment | Identify supply gaps, source eligible vendors, create POs with contract terms, receive goods, and close POs. |  | Medium | 8 | 60 | 1 | 3
DEL-009 | FOUNDATIONS | BP-1765865704672 | PH-01 | Foundation | Foundations | Infrastructure and foundational systems |  |  |  | 160 | 6 | 18
DEL-010 | FUNC-031 | BP-1765865704672 | PH-01 | Integration | Inventory / WMS Service | Source of truth for on-hand/available inventory and the execution surface for reservations and receiving updates. |  | High | 8 | 40 | 1 | 1
DEL-011 | FUNC-032 | BP-1765865704672 | PH-01 | Integration | Vendor Portal / Supplier API | External vendor system(s) providing item availability, lead times, SLAs, and certification status for sourcing and substitution decisions. |  | High | 8 | 60 | 1 | 1
DEL-012 | FUNC-033 | BP-1765865704672 | PH-01 | Integration | Compliance Rules & Restrictions Service | External or internal service that returns compliance rules, geo restrictions, and item-level regulatory attributes for evaluation at order and substitution time. |  | High | 8 | 60 | 1 | 1
DEL-013 | FUNC-034 | BP-1765865704672 | PH-01 | Integration | Messaging / Event Bus | Central eventing platform used to publish OMS domain events for consumers (ERP integration workers, dashboards, notifications). |  | Medium | 5 | 40 | 1 | 1

## EPIC - Epics
Epic ID | Strategy Ref | Blueprint Ref | Phase Ref ID | Deliverable ID | Deliverable Name | Epic Type | Epic Name | Epic User Story | Notes | Complexity | Effort | Hours | ELI Roll-Up
EPIC-001 | CAP-006 | BP-1765865704672 | PH-01 | DEL-006 | Sales Order Processing | Workflow | Sales Order Processing | Create, validate, price, and route sales orders through approvals to a “ready for fulfillment” state with full auditability. |  | High | 13 |  | 5
EPIC-002 | CAP-007 | BP-1765865704672 | PH-01 | DEL-007 | Fulfillment Execution | Workflow | Fulfillment Execution | Route fulfillment, allocate inventory, generate pick/pack/ship instructions, and confirm shipment with auditability. |  | High | 13 |  | 5
EPIC-003 | CAP-008 | BP-1765865704672 | PH-01 | DEL-008 | Purchase Replenishment | Workflow | Purchase Replenishment | Identify supply gaps, source eligible vendors, create POs with contract terms, receive goods, and close POs. |  | Medium | 8 |  | 3
EPIC-004 | CAP-014 | BP-1765865704672 | PH-01 | DEL-009 | Foundations | Foundation | Navigation and Component Library | Establish the visual framework and reusable building blocks that define the application's user experience across OMS screens. |  | Medium | 8 |  | 3
EPIC-005 | CAP-015 | BP-1765865704672 | PH-01 | DEL-009 | Foundations | Foundation | User Management | Set up systems to onboard, store, and manage user accounts so each OMS user has an identity tied to permissions and settings. |  | Medium | 8 |  | 3
EPIC-006 | CAP-016 | BP-1765865704672 | PH-01 | DEL-009 | Foundations | Foundation | Authentication & Security | Protect OMS access with secure login flows, API protection, and encryption for sensitive contract, pricing, and compliance data. |  | High | 13 |  | 3
EPIC-007 | CAP-017 | BP-1765865704672 | PH-01 | DEL-009 | Foundations | Foundation | Data Management | Establish OMS core data models and APIs to support customers, contracts, orders, inventory reservations, fulfillment events, and purchasing. |  | High | 13 |  | 3
EPIC-008 | CAP-018 | BP-1765865704672 | PH-01 | DEL-009 | Foundations | Foundation | Backend Infrastructure | Provide core runtime, APIs, messaging, observability, and operational safeguards required to run OMS reliably across workflows and integrations. |  | High | 13 |  | 3
EPIC-009 | CAP-019 | BP-1765865704672 | PH-01 | DEL-009 | Foundations | Foundation | DevOps | Enable smooth development, deployment, and maintenance workflows across environments (local, staging, production) for OMS. |  | Medium | 8 |  | 3
EPIC-010 | FUNC-001 | BP-1765865704672 | PH-01 | DEL-001 | Customer Management | Use Case | Manage Customers | Create, update, and search customer profiles used for order association and downstream enforcement. |  | Medium | 5 |  | 3
EPIC-011 | FUNC-002 | BP-1765865704672 | PH-01 | DEL-001 | Customer Management | Use Case | Associate Contracts to Customers | Link active contracts to customers so pricing, terms, and decisioning are enforced at order time. |  | High | 8 |  | 3
EPIC-012 | FUNC-003 | BP-1765865704672 | PH-01 | DEL-001 | Customer Management | Use Case | Manage Customer Compliance Requirements | Define and apply customer-specific compliance constraints and maintain an auditable trail of compliance decisions. |  | High | 8 |  | 3
EPIC-013 | FUNC-004 | BP-1765865704672 | PH-01 | DEL-002 | Inventory Management | Use Case | Manage Inventory | View, adjust, and receive inventory to keep system state aligned with physical reality. |  | Medium | 5 |  | 3
EPIC-014 | FUNC-005 | BP-1765865704672 | PH-01 | DEL-002 | Inventory Management | Use Case | Track Inventory Availability Across Sources | Track inventory signals across warehouses and vendors with clear source attribution and allocatability. |  | Medium | 5 |  | 3
EPIC-015 | FUNC-006 | BP-1765865704672 | PH-01 | DEL-002 | Inventory Management | Use Case | Allocate Inventory to Orders | Reserve, release, and reallocate inventory to maintain accurate commitments and prevent double-allocation. |  | High | 8 |  | 3
EPIC-016 | FUNC-007 | BP-1765865704672 | PH-01 | DEL-003 | Order Management | Use Case | Create Sales Order | Create sales orders tied to customer contract context with completeness validation and pricing preview. |  | Medium | 5 |  | 3
EPIC-017 | FUNC-008 | BP-1765865704672 | PH-01 | DEL-003 | Order Management | Use Case | Evaluate Contract Pricing & Terms | Calculate and enforce contract pricing, tiers, rebates, penalties, and recalculation on changes. |  | High | 8 |  | 3
EPIC-018 | FUNC-009 | BP-1765865704672 | PH-01 | DEL-003 | Order Management | Use Case | Manage Sales Order Lifecycle | View, update, and cancel orders with auditable lifecycle state transitions. |  | Medium | 5 |  | 3
EPIC-019 | FUNC-010 | BP-1765865704672 | PH-01 | DEL-003 | Order Management | Use Case | Approve Order Exceptions & Overrides | Route, decide, and audit approvals for threshold breaches and controlled overrides. |  | High | 8 |  | 3
EPIC-020 | FUNC-011 | BP-1765865704672 | PH-01 | DEL-004 | Fulfillment Orchestration | Use Case | Execute Fulfillment | Assign, pick, pack, and ship with system-generated instructions and dispatch tracking. |  | Medium | 5 |  | 3
EPIC-021 | FUNC-012 | BP-1765865704672 | PH-01 | DEL-004 | Fulfillment Orchestration | Use Case | Determine Fulfillment Routing | Select optimal routing across warehouses/vendors, including order splitting and SLA constraints. |  | High | 8 |  | 3
EPIC-022 | FUNC-013 | BP-1765865704672 | PH-01 | DEL-004 | Fulfillment Orchestration | Use Case | Validate Regulated Substitutions | Propose and validate substitutions against contract permissions, vendor certifications, and regulatory/geographic constraints. |  | High | 8 |  | 3
EPIC-023 | FUNC-014 | BP-1765865704672 | PH-01 | DEL-005 | Purchase Management | Use Case | Create Purchase Order | Create purchase orders from demand signals with approved vendor selection and applied contract terms. |  | Medium | 5 |  | 3
EPIC-024 | FUNC-015 | BP-1765865704672 | PH-01 | DEL-005 | Purchase Management | Use Case | Receive Purchase Order | Receive goods against purchase orders with discrepancy handling and closure. |  | Medium | 5 |  | 3
EPIC-025 | FUNC-016 | BP-1765865704672 | PH-01 | DEL-005 | Purchase Management | Use Case | Source Supply from Vendors | Evaluate vendor eligibility and select optimal sources based on compliance, lead times, SLAs, and rules. |  | High | 8 |  | 3
EPIC-026 | FUNC-031 | BP-1765865704672 | PH-01 | DEL-010 | Inventory / WMS Service | System | Inventory / WMS Service | Source of truth for on-hand/available inventory and the execution surface for reservations and receiving updates. |  | High | 8 |  | 1
EPIC-027 | FUNC-032 | BP-1765865704672 | PH-01 | DEL-011 | Vendor Portal / Supplier API | System | Vendor Portal / Supplier API | External vendor system(s) providing item availability, lead times, SLAs, and certification status for sourcing and substitution decisions. |  | High | 8 |  | 1
EPIC-028 | FUNC-033 | BP-1765865704672 | PH-01 | DEL-012 | Compliance Rules & Restrictions Service | System | Compliance Rules & Restrictions Service | External or internal service that returns compliance rules, geo restrictions, and item-level regulatory attributes for evaluation at order and substitution time. |  | High | 8 |  | 1
EPIC-029 | FUNC-034 | BP-1765865704672 | PH-01 | DEL-013 | Messaging / Event Bus | System | Messaging / Event Bus | Central eventing platform used to publish OMS domain events for consumers (ERP integration workers, dashboards, notifications). |  | Medium | 5 |  | 1

## UG - User Groups
User Group ID | Name | Description | Objectives | Challenges | Benefits | High Level User Story
UG-01 | Sales / Account Management | Owns customer relationships and initiates sales orders, ensuring accurate customer context, pricing visibility, and contract alignment at order time. | Create and submit accurate sales orders quickly; Ensure contract pricing is applied correctly on first pass; Respond confidently to customer questions and changes | Contract logic historically scattered across spreadsheets and emails; Risk of quoting incorrect pricing or terms; Dependence on Ops or Finance for validations | Faster order entry with fewer escalations; Higher order accuracy and customer trust; Clear visibility into pricing and approvals | As a/An Sales / Account Management, I want Create and submit accurate sales orders quickly so that Faster order entry with fewer escalations.
UG-02 | Operations / Order Management | Orchestrates order execution and exception handling, translating complex business rules into consistent fulfillment outcomes. | Execute complex orders with system-driven decisions; Reduce manual intervention and operational firefighting; Ensure routing, sourcing, and substitutions follow rules and SLAs | Reliance on tribal knowledge for fulfillment decisions; Multi-source fulfillment complexity; Frequent exceptions requiring rework | Repeatable and predictable order execution; Fewer escalations and handoffs; Clear audit trail for operational decisions | As a/An Operations / Order Management, I want Execute complex orders with system-driven decisions so that Repeatable and predictable order execution.
UG-03 | Warehouse & Fulfillment | Executes picking, packing, shipping, and receiving activities across warehouses using system-generated instructions. | Fulfill orders accurately and efficiently; Maintain inventory accuracy through timely updates; Execute substitutions and splits correctly | Limited visibility into upstream decision context; Increased error risk from multi-warehouse splits; Inventory discrepancies due to delayed updates | Clear pick/pack/ship instructions; Reduced fulfillment errors and rework; Faster throughput and inventory accuracy | As a/An Warehouse & Fulfillment, I want Fulfill orders accurately and efficiently so that Clear pick/pack/ship instructions.
UG-04 | Finance / Compliance / Admin | Governs pricing, approvals, compliance, and auditability to protect margins, ensure regulatory adherence, and maintain system integrity. | Enforce contract pricing, approvals, and overrides; Maintain audit-ready records for pricing and compliance; Govern changes to contracts, rules, and vendors safely | Margin erosion detected too late in the process; Manual audit preparation using spreadsheets; Risk when critical logic lives outside core systems | Predictable margin protection; Clear, defensible audit trails; Centralized governance of rules and decisions | As a/An Finance / Compliance / Admin, I want Enforce contract pricing, approvals, and overrides so that Predictable margin protection.

## User Stories
ELI ID | deliverable | epic | Description | as the | I want to | so i can | Phase | Tech Notes | complexity | hours | sa | qa | total
ELI-001 | Customer Management | Manage Customers | As a Sales user, I want to create a customer profile so that orders can be associated with the correct legal and billing entity. | Sales / Account Management | create a customer profile | orders can be associated with the correct legal and billing entity. | PH-01 |  | Medium | 12 | 3 | 1 | 16
ELI-002 | Customer Management | Manage Customers | As a Sales user, I want to update customer details so changes are reflected in future orders. | Sales / Account Management | update customer details | changes are reflected in future orders | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-003 | Customer Management | Manage Customers | As an Ops user, I want to search customers quickly so I can validate order context without manual lookup. | Operations / Order Management | search customers quickly | validate order context without manual lookup. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-004 | Customer Management | Associate Contracts to Customers | As an Admin, I want to associate an active contract to a customer so pricing and terms are enforced at order time. | Finance / Compliance / Admin | associate an active contract to a customer | pricing and terms are enforced at order time. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-005 | Customer Management | Associate Contracts to Customers | As Finance, I want to prevent orders for customers without active contracts to avoid uncontrolled pricing. | Finance / Compliance / Admin | prevent orders for customers without active contracts | avoid uncontrolled pricing | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-006 | Customer Management | Associate Contracts to Customers | As Finance, I want to view contract assignment history so audits do not rely on spreadsheets. | Finance / Compliance / Admin | view contract assignment history | audits do not rely on spreadsheets. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-007 | Customer Management | Manage Customer Compliance Requirements | As a Compliance admin, I want to define customer-specific compliance rules so non-compliant orders are blocked. | Finance / Compliance / Admin | define customer-specific compliance rules | non-compliant orders are blocked. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-008 | Customer Management | Manage Customer Compliance Requirements | As Ops, I want compliance rules evaluated automatically so I don’t interpret regulations manually. | Operations / Order Management | compliance rules evaluated automatically | I don’t interpret regulations manually. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-009 | Customer Management | Manage Customer Compliance Requirements | As Compliance, I want an audit trail of compliance decisions so regulatory reviews are defensible. | Finance / Compliance / Admin | want an audit trail of compliance decisions | regulatory reviews are defensible | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-010 | Inventory Management | Manage Inventory | As an Ops user, I want to view real-time inventory levels so I can make accurate fulfillment decisions. | Operations / Order Management | view real-time inventory levels | so I can make accurate fulfillment decisions. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-011 | Inventory Management | Manage Inventory | As a Warehouse user, I want to adjust inventory quantities so physical discrepancies are reflected in the system. | Warehouse & Fulfillment | adjust inventory quantities | physical discrepancies are reflected in the system. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-012 | Inventory Management | Manage Inventory | As a Warehouse user, I want to receive inventory so newly arrived stock becomes available for allocation. | Warehouse & Fulfillment | receive inventory | newly arrived stock becomes available for allocation. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-013 | Inventory Management | Track Inventory Availability Across Sources | As Ops, I want to see inventory across all warehouses so I can plan multi-location fulfillment. | Operations / Order Management | see inventory across all warehouses | plan multi-location fulfillment. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-014 | Inventory Management | Track Inventory Availability Across Sources | As Ops, I want vendor-supplied availability included so out-of-stock items can still be sourced compliantly. | Operations / Order Management | include vendor-supplied availability | so out-of-stock items can still be sourced compliantly. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-015 | Inventory Management | Track Inventory Availability Across Sources | As Finance, I want to distinguish allocatable inventory from informational stock so financial exposure is controlled. | Finance / Compliance / Admin | distinguish allocatable inventory from informational stock | financial exposure is controlled. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-016 | Inventory Management | Allocate Inventory to Orders | As Ops, I want to reserve inventory so stock is protected for committed orders. | Operations / Order Management | reserve inventory | stock is protected for committed orders. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-017 | Inventory Management | Allocate Inventory to Orders | As Ops, I want reserved inventory released when an order is canceled so stock is reusable. | Operations / Order Management | reserved inventory released when an order is canceled | stock is reusable | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-018 | Inventory Management | Allocate Inventory to Orders | As Ops, I want inventory reallocated when orders change so fulfillment remains accurate. | Operations / Order Management | I want inventory reallocated when orders change | fulfillment remains accurate | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-019 | Order Management | Create Sales Order | As a Sales user, I want to create a sales order tied to a customer so contract pricing and rules are applied automatically. | Sales / Account Management | create a sales order tied to a customer | contract pricing and rules are applied automatically. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-020 | Order Management | Create Sales Order | As a Sales user, I want required order data validated so incomplete orders cannot proceed. | Sales / Account Management | required order data validated | incomplete orders cannot proceed. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-021 | Order Management | Create Sales Order | As a Sales user, I want to preview pricing so I can confirm totals before submitting the order. | Sales / Account Management | preview pricing | confirm totals before submitting the order. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-022 | Order Management | Evaluate Contract Pricing & Terms | As Finance, I want tiered pricing applied automatically so pricing is consistent and auditable. | Finance / Compliance / Admin | apply tiered pricing automatically | pricing is consistent and auditable. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-023 | Order Management | Evaluate Contract Pricing & Terms | As Finance, I want rebates and penalties enforced so margins and commitments are protected. | Finance / Compliance / Admin | rebates and penalties enforced | margins and commitments are protected. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-024 | Order Management | Evaluate Contract Pricing & Terms | As Ops, I want pricing recalculated when an order changes so pricing remains accurate. | Operations / Order Management | recalculated when an order changes | pricing remains accurate. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-025 | Order Management | Manage Sales Order Lifecycle | As Ops, I want to view order status so I can track progress without manual follow-up. | Operations / Order Management | view order status | track progress without manual follow-up. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-026 | Order Management | Manage Sales Order Lifecycle | As Ops, I want to update order status so downstream processes stay aligned. | Operations / Order Management | update order status | downstream processes stay aligned | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-027 | Order Management | Manage Sales Order Lifecycle | As Sales, I want to cancel an order so inventory and commitments are released correctly. | Sales / Account Management | cancel an order | inventory and commitments are released correctly. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-028 | Order Management | Approve Order Exceptions & Overrides | As Finance, I want orders that exceed thresholds routed for approval so risk is controlled. | Finance / Compliance / Admin | orders that exceed thresholds routed for approval | risk is controlled | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-029 | Order Management | Approve Order Exceptions & Overrides | As Finance, I want to approve or reject exceptions so decisions are explicit and traceable. | Finance / Compliance / Admin | approve or reject exceptions | decisions are explicit and traceable. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-030 | Order Management | Approve Order Exceptions & Overrides | As Finance, I want an audit trail of approvals so reviews do not rely on email chains. | Finance / Compliance / Admin | view an audit trail of approvals | reviews do not rely on email chains. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-031 | Fulfillment Orchestration | Execute Fulfillment | As Ops, I want orders assigned to the appropriate fulfillment resource so execution begins without manual routing. | Operations / Order Management | orders assigned to the appropriate fulfillment resource | execution begins without manual routing. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-032 | Fulfillment Orchestration | Execute Fulfillment | As a Warehouse user, I want system-generated pick instructions so I can fulfill orders accurately. | Warehouse & Fulfillment | system-generated pick instructions | fulfill orders accurately. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-033 | Fulfillment Orchestration | Execute Fulfillment | As a Warehouse user, I want to pack and ship orders so delivery proceeds according to service levels. | Warehouse & Fulfillment | pack and ship orders | delivery proceeds according to service levels. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-034 | Fulfillment Orchestration | Determine Fulfillment Routing | As Ops, I want the system to select the optimal fulfillment path so cost and SLA requirements are met. | Operations / Order Management | select the optimal fulfillment path | cost and SLA requirements are met. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-035 | Fulfillment Orchestration | Determine Fulfillment Routing | As Ops, I want orders split across sources when necessary so commitments are met. | Operations / Order Management | split orders across sources when necessary | commitments are met | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-036 | Fulfillment Orchestration | Determine Fulfillment Routing | As Finance, I want service-level constraints enforced so contractual obligations are met. | Finance / Compliance / Admin | service-level constraints enforced | contractual obligations are met. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-037 | Fulfillment Orchestration | Validate Regulated Substitutions | As Ops, I want the system to propose allowed substitutions so I don’t manually assess eligibility. | Operations / Order Management | the system to propose allowed substitutions | I don't manually assess eligibility. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-038 | Fulfillment Orchestration | Validate Regulated Substitutions | As Compliance, I want vendor certifications validated so non-compliant substitutions are blocked. | Finance / Compliance / Admin | vendor certifications validated | non-compliant substitutions are blocked. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-039 | Fulfillment Orchestration | Validate Regulated Substitutions | As Compliance, I want geographic and regulatory rules enforced so orders comply with applicable laws. | Finance / Compliance / Admin | geographic and regulatory rules enforced | orders comply with applicable laws. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-040 | Purchase Management | Create Purchase Order | As Ops, I want to generate a purchase order from unmet demand so supply gaps are addressed quickly. | Operations / Order Management | generate a purchase order from unmet demand | supply gaps are addressed quickly. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-041 | Purchase Management | Create Purchase Order | As Finance, I want only approved vendors selectable so compliance and pricing terms are enforced. | Finance / Compliance / Admin | only approved vendors selectable | compliance and pricing terms are enforced. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-042 | Purchase Management | Create Purchase Order | As Finance, I want vendor contract terms applied so purchasing aligns with negotiated pricing and penalties. | Finance / Compliance / Admin | apply vendor contract terms | purchasing aligns with negotiated pricing and penalties. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-043 | Purchase Management | Receive Purchase Order | As a Warehouse user, I want to receive goods against a PO so inventory updates accurately. | Warehouse & Fulfillment | receive goods against a PO | inventory updates accurately | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-044 | Purchase Management | Receive Purchase Order | As a Warehouse user, I want to record partial or over-receipt so discrepancies are tracked. | Warehouse & Fulfillment | record partial or over-receipt | discrepancies are tracked. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-045 | Purchase Management | Receive Purchase Order | As Ops, I want POs closed after receipt so purchasing status remains accurate. | Operations / Order Management | POs closed after receipt | purchasing status remains accurate. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-046 | Purchase Management | Source Supply from Vendors | As Compliance, I want vendor eligibility evaluated so sourcing complies with certifications and risk policies. | Finance / Compliance / Admin | vendor eligibility evaluated | sourcing complies with certifications and risk policies. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-047 | Purchase Management | Source Supply from Vendors | As Ops, I want to compare vendor lead times and SLAs so sourcing decisions meet fulfillment needs. | Operations / Order Management | compare vendor lead times and SLAs | sourcing decisions meet fulfillment needs. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-048 | Purchase Management | Source Supply from Vendors | As Ops, I want the system to select the optimal vendor so cost, compliance, and delivery goals are balanced. | Operations / Order Management | select the optimal vendor | cost, compliance, and delivery goals are balanced. | PH-01 |  | Medium | 12 | 3 | 5 | 20
ELI-049 | Sales Order Processing | Sales Order Processing | Capture order header and lines tied to a customer context. | N/A | Capture order header and lines tied to a customer context. | This description does not follow the standard "As a... I want to... so I can..." format. The goal of this story is "Capture order header and lines tied to a customer context." Since there is no "so I can" clause, I cannot extract the value. | PH-01 |  | Medium | 20 | 4 | 8 | 32
ELI-050 | Sales Order Processing | Sales Order Processing | Resolve active contract(s) and customer compliance requirements for this order. | N/A | Resolve active contract(s) and customer compliance requirements for this order. | Ensure terms are consistent and auditable, and non-compliant orders are blocked. | PH-01 |  | High | 32 | 7 | 13 | 52
ELI-051 | Sales Order Processing | Sales Order Processing | Apply tiered pricing, rebates/penalties, and ensure terms are consistent and auditable. | N/A | Apply tiered pricing, rebates/penalties, and ensure terms are consistent and auditable. | ensure terms are consistent and auditable. | PH-01 |  | High | 32 | 7 | 13 | 52
ELI-052 | Sales Order Processing | Sales Order Processing | Identify orders requiring approval and route to Finance/Admin for decision. | N/A | Identify orders requiring approval and route to Finance/Admin for decision. | for decision. | PH-01 |  | Medium | 20 | 4 | 8 | 32
ELI-053 | Sales Order Processing | Sales Order Processing | Transition approved orders to a fulfillment-ready state and emit downstream signals. | N/A | Transition approved orders to a fulfillment-ready state and emit downstream signals. | emit downstream signals | PH-01 |  | Medium | 20 | 4 | 8 | 32
ELI-054 | Fulfillment Execution | Fulfillment Execution | Choose warehouse/vendor sources and split the order when needed to meet SLAs and rules. | N/A | Choose warehouse/vendor sources and split the order when needed | meet SLAs and rules. | PH-01 |  | High | 32 | 7 | 13 | 52
ELI-055 | Fulfillment Execution | Fulfillment Execution | Reserve inventory for the chosen sources and prevent double-allocation. | N/A | Reserve inventory for the chosen sources and prevent double-allocation. | prevent double-allocation. | PH-01 |  | High | 32 | 7 | 13 | 52
ELI-056 | Fulfillment Execution | Fulfillment Execution | Validate substitutions against contracts, certifications, and geographic/regulatory constraints. | N/A | Validate substitutions against contracts, certifications, and geographic/regulatory constraints. | ensure compliance with contracts, certifications, and geographic/regulatory constraints. | PH-01 |  | High | 32 | 7 | 13 | 52
ELI-057 | Fulfillment Execution | Fulfillment Execution | Produce actionable fulfillment instructions for warehouse execution. | N/A | Produce actionable fulfillment instructions | for warehouse execution. | PH-01 |  | Medium | 20 | 4 | 8 | 32
ELI-058 | Fulfillment Execution | Fulfillment Execution | Mark shipments dispatched, attach tracking, and update order lifecycle state. | N/A | Mark shipments dispatched, attach tracking, and update order lifecycle state. | Efficient and accurate tracking of the order through its lifecycle. | PH-01 |  | Medium | 20 | 4 | 8 | 32
ELI-059 | Purchase Replenishment | Purchase Replenishment | Identify when demand exceeds available inventory and triggers purchasing. | N/A | Identify when demand exceeds available inventory and triggers purchasing. | triggers purchasing | PH-01 |  | Medium | 20 | 4 | 8 | 32
ELI-060 | Purchase Replenishment | Purchase Replenishment | Ensure vendor eligibility and select optimal vendor based on lead times and rules. | N/A | Ensure vendor eligibility and select optimal vendor based on lead times and rules. | based on lead times and rules. | PH-01 |  | Medium | 20 | 4 | 8 | 32
ELI-061 | Purchase Replenishment | Purchase Replenishment | Create PO with applied vendor contract terms and required delivery dates. | N/A | Create PO with applied vendor contract terms and required delivery dates. | applied vendor contract terms and required delivery dates | PH-01 |  | Medium | 20 | 4 | 8 | 32
ELI-062 | Inventory / WMS Service | Inventory / WMS Service | Source of truth for on-hand/available inventory and the execution surface for reservations and receiving updates. | N/A | be the source of truth for on-hand/available inventory and the execution surface for reservations and receiving updates | on-hand/available inventory and the execution surface for reservations and receiving updates. | PH-01 |  | High | 32 | 7 | 13 | 52
ELI-063 | Vendor Portal / Supplier API | Vendor Portal / Supplier API | External vendor system(s) providing item availability, lead times, SLAs, and certification status for sourcing and substitution decisions. | N/A | Provide item availability, lead times, SLAs, and certification status for sourcing and substitution decisions | for sourcing and substitution decisions. | PH-01 |  | High | 32 | 7 | 13 | 52
ELI-064 | Compliance Rules & Restrictions Service | Compliance Rules & Restrictions Service | External or internal service that returns compliance rules, geo restrictions, and item-level regulatory attributes for evaluation at order and substitution time. | N/A | returns compliance rules, geo restrictions, and item-level regulatory attributes for evaluation at order and substitution time. | evaluation at order and substitution time. | PH-01 |  | High | 32 | 7 | 13 | 52
ELI-065 | Messaging / Event Bus | Messaging / Event Bus | Central eventing platform used to publish OMS domain events for consumers (ERP integration workers, dashboards, notifications). | N/A | publish OMS domain events for consumers (ERP integration workers, dashboards, notifications) | consumers (ERP integration workers, dashboards, notifications) | PH-01 |  | Medium | 20 | 4 | 8 | 32
ELI-066 | Foundations | Navigation and Component Library | Choose and install a design system | N/A | Choose and install a design system | This description does not contain a specific "so I can" value/outcome. | PH-01 |  | Medium | 20 | 4 | 8 | 32
ELI-067 | Foundations | Navigation and Component Library | Define dashboard shell, sidebar, headers, and modal containers. | N/A | define dashboard shell, sidebar, headers, and modal containers | No explicit value is stated. | PH-01 |  | Medium | 20 | 4 | 8 | 32
ELI-068 | Foundations | Navigation and Component Library | Set up route configuration and page access logic | N/A | Set up route configuration and page access logic | application can function correctly and securely | PH-01 |  | Medium | 20 | 4 | 8 | 32
ELI-069 | Foundations | User Management | Define core fields like name, email, auth method, and settings. | N/A | Define core fields like name, email, auth method, and settings. | The description itself is the goal (to define core fields). There is no explicit "so I can" value statement in the description provided. If this is a technical task, the value is inherent in setting up the foundational data structure for users. | PH-01 |  | Medium | 20 | 4 | 8 | 32
ELI-070 | Foundations | User Management | Allow users to update their information, timezone, and avatar. | N/A | Allow users to update their information, timezone, and avatar. | Extracting the "so I can" value from the phrase "Allow users to update their information, timezone, and avatar" does not produce a meaningful benefit as it stands alone and is not a complete user story following the "As a... I want... so I can..." format. I will assume the intended request is to extract the goal, which is the action the user wants to perform. users update their information, timezone, and avatar | PH-01 |  | Low | 12 | 3 | 5 | 20
ELI-071 | Foundations | User Management | Log login history, session duration, and access activity. | N/A | Log login history, session duration, and access activity. | No explicit value is stated in the provided text, as it describes the action itself. | PH-01 |  | Medium | 20 | 4 | 8 | 32
ELI-072 | Foundations | Authentication & Security | Integrate platforms like Auth0, Clerk, or Firebase Auth. | N/A | Integrate platforms like Auth0, Clerk, or Firebase Auth. | Ensure a secure and robust authentication system. | PH-01 |  | Medium | 20 | 4 | 8 | 32
ELI-073 | Foundations | Authentication & Security | Use JWTs or sessions to authorize requests on protected endpoints. | N/A | authorize requests on protected endpoints | authorize requests on protected endpoints | PH-01 |  | High | 32 | 7 | 13 | 52
ELI-074 | Foundations | Authentication & Security | Encrypt sensitive data both in transit (HTTPS) and at rest (AES). | N/A | Encrypt sensitive data both in transit (HTTPS) and at rest (AES). | To protect sensitive data and ensure security. | PH-01 |  | High | 32 | 7 | 13 | 52
ELI-075 | Foundations | Data Management | Model core data object of the system | N/A | Model core data object of the system | Model core data object of the system | PH-01 |  | High | 32 | 7 | 13 | 52
ELI-076 | Foundations | Data Management | Expose backend endpoints for accessing and modifying | N/A | expose backend endpoints for accessing and modifying | for accessing and modifying | PH-01 |  | Medium | 20 | 4 | 8 | 32
ELI-077 | Foundations | Data Management | Capture a change log for critical actions like edits, deletions, or merges. | N/A | Capture a change log for critical actions like edits, deletions, or merges. | This description appears to be missing the "as the" and "so I can" structure. Based on the provided description, "Capture a change log for critical actions like edits, deletions, or merges.", the value is implied to be for auditing or data integrity. I am unable to accurately extract the value when the user story format is not present in the description. | PH-01 |  | High | 32 | 7 | 13 | 52
ELI-078 | Foundations | Backend Infrastructure | Centralize request routing, versioning, throttling, and request/response transformations for REST/GraphQL. | N/A | Centralize request routing, versioning, throttling, and request/response transformations for REST/GraphQL | efficiently manage and scale API traffic | PH-01 |  | Medium | 20 | 4 | 8 | 32
ELI-079 | Foundations | Backend Infrastructure | Support async jobs, scheduled work, and event-driven workflows (e.g., retries, dead-letter queues). | N/A | Support async jobs, scheduled work, and event-driven workflows (e.g., retries, dead-letter queues). | e.g., retries, dead-letter queues. | PH-01 |  | High | 32 | 7 | 13 | 52
ELI-080 | Foundations | Backend Infrastructure | Collect logs, metrics, and traces with correlation IDs and alerting thresholds. | N/A | collect logs, metrics, and traces with correlation IDs and alerting thresholds | with correlation IDs and alerting thresholds. | PH-01 |  | Medium | 20 | 4 | 8 | 32
ELI-081 | Foundations | DevOps | Use .env files and secrets management for tokens, keys, and DB strings. | N/A | Use .env files and secrets management for tokens, keys, and DB strings. | Ensure sensitive data is protected and deployment is secure. | PH-01 |  | Medium | 20 | 4 | 8 | 32
ELI-082 | Foundations | DevOps | Deploy with GitHub Actions, Vercel, or custom workflows for build/test/release. | N/A | Deploy with GitHub Actions, Vercel, or custom workflows for build/test/release. | for build/test/release. | PH-01 |  | Medium | 20 | 4 | 8 | 32
ELI-083 | Foundations | DevOps | Integrate unit, integration, and end-to-end test pipelines. | N/A | Integrate unit, integration, and end-to-end test pipelines. | The description "Integrate unit, integration, and end-to-end test pipelines." is a technical task and does not explicitly state the value/benefit. | PH-01 |  | Medium | 20 | 4 | 8 | 32
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## ELI Data File
ELI ID | Strategy Ref | Blueprint Ref | Phase Ref ID | Deliverable ID | Epic ID | User Group ID | User Group Name | Deliverable Name | Epic Name | ELI Name | ELI Type | ELI Description | Notes | Complexity | Effort | Tech Hours | SA Hours
ELI-001 | FUNC-001 | BP-1765865704672 | PH-01 | DEL-001 | EPIC-010 |  | Sales / Account Management | Customer Management | Manage Customers | Create a Customer Profile | User Story | As a Sales user, I want to create a customer profile so that orders can be associated with the correct legal and billing entity. |  | Medium | 3 | 4 | 0.8
ELI-002 | FUNC-001 | BP-1765865704672 | PH-01 | DEL-001 | EPIC-010 |  | Sales / Account Management | Customer Management | Manage Customers | Update Customer Information | User Story | As a Sales user, I want to update customer details so changes are reflected in future orders. |  | Medium | 3 | 4 | 0.8
ELI-003 | FUNC-001 | BP-1765865704672 | PH-01 | DEL-001 | EPIC-010 |  | Operations / Order Management | Customer Management | Manage Customers | Search and Retrieve Customers | User Story | As an Ops user, I want to search customers quickly so I can validate order context without manual lookup. |  | Medium | 3 | 4 | 0.8
ELI-004 | FUNC-002 | BP-1765865704672 | PH-01 | DEL-001 | EPIC-011 |  | Finance / Compliance / Admin | Customer Management | Associate Contracts to Customers | Link Active Contract to Customer | User Story | As an Admin, I want to associate an active contract to a customer so pricing and terms are enforced at order time. |  | Medium | 3 |  | 0
ELI-005 | FUNC-002 | BP-1765865704672 | PH-01 | DEL-001 | EPIC-011 |  | Finance / Compliance / Admin | Customer Management | Associate Contracts to Customers | Prevent Orders Without Active Contracts | User Story | As Finance, I want to prevent orders for customers without active contracts to avoid uncontrolled pricing. |  | Medium | 3 |  | 0
ELI-006 | FUNC-002 | BP-1765865704672 | PH-01 | DEL-001 | EPIC-011 |  | Finance / Compliance / Admin | Customer Management | Associate Contracts to Customers | View Contract Association History | User Story | As Finance, I want to view contract assignment history so audits do not rely on spreadsheets. |  | Medium | 3 |  | 0
ELI-007 | FUNC-003 | BP-1765865704672 | PH-01 | DEL-001 | EPIC-012 |  | Finance / Compliance / Admin | Customer Management | Manage Customer Compliance Requirements | Define Customer Compliance Constraints | User Story | As a Compliance admin, I want to define customer-specific compliance rules so non-compliant orders are blocked. |  | Medium | 3 |  | 0
ELI-008 | FUNC-003 | BP-1765865704672 | PH-01 | DEL-001 | EPIC-012 |  | Operations / Order Management | Customer Management | Manage Customer Compliance Requirements | Apply Compliance Rules at Order Time | User Story | As Ops, I want compliance rules evaluated automatically so I don’t interpret regulations manually. |  | Medium | 3 |  | 0
ELI-009 | FUNC-003 | BP-1765865704672 | PH-01 | DEL-001 | EPIC-012 |  | Finance / Compliance / Admin | Customer Management | Manage Customer Compliance Requirements | Audit Customer Compliance Decisions | User Story | As Compliance, I want an audit trail of compliance decisions so regulatory reviews are defensible. |  | Medium | 3 |  | 0
ELI-010 | FUNC-004 | BP-1765865704672 | PH-01 | DEL-002 | EPIC-013 |  | Operations / Order Management | Inventory Management | Manage Inventory | View Real-Time Inventory Levels | User Story | As an Ops user, I want to view real-time inventory levels so I can make accurate fulfillment decisions. |  | Medium | 3 |  | 0
ELI-011 | FUNC-004 | BP-1765865704672 | PH-01 | DEL-002 | EPIC-013 |  | Warehouse & Fulfillment | Inventory Management | Manage Inventory | Adjust Inventory Quantity | User Story | As a Warehouse user, I want to adjust inventory quantities so physical discrepancies are reflected in the system. |  | Medium | 3 |  | 0
ELI-012 | FUNC-004 | BP-1765865704672 | PH-01 | DEL-002 | EPIC-013 |  | Warehouse & Fulfillment | Inventory Management | Manage Inventory | Receive Inventory Into Stock | User Story | As a Warehouse user, I want to receive inventory so newly arrived stock becomes available for allocation. |  | Medium | 3 |  | 0
ELI-013 | FUNC-005 | BP-1765865704672 | PH-01 | DEL-002 | EPIC-014 |  | Operations / Order Management | Inventory Management | Track Inventory Availability Across Sources | View Inventory Across Warehouses | User Story | As Ops, I want to see inventory across all warehouses so I can plan multi-location fulfillment. |  | Medium | 3 |  | 0
ELI-014 | FUNC-005 | BP-1765865704672 | PH-01 | DEL-002 | EPIC-014 |  | Operations / Order Management | Inventory Management | Track Inventory Availability Across Sources | Include Vendor-Supplied Availability | User Story | As Ops, I want vendor-supplied availability included so out-of-stock items can still be sourced compliantly. |  | Medium | 3 |  | 0
ELI-015 | FUNC-005 | BP-1765865704672 | PH-01 | DEL-002 | EPIC-014 |  | Finance / Compliance / Admin | Inventory Management | Track Inventory Availability Across Sources | Distinguish Allocatable vs Informational Stock | User Story | As Finance, I want to distinguish allocatable inventory from informational stock so financial exposure is controlled. |  | Medium | 3 |  | 0
ELI-016 | FUNC-006 | BP-1765865704672 | PH-01 | DEL-002 | EPIC-015 |  | Operations / Order Management | Inventory Management | Allocate Inventory to Orders | Reserve Inventory for an Order | User Story | As Ops, I want to reserve inventory so stock is protected for committed orders. |  | Medium | 3 |  | 0
ELI-017 | FUNC-006 | BP-1765865704672 | PH-01 | DEL-002 | EPIC-015 |  | Operations / Order Management | Inventory Management | Allocate Inventory to Orders | Release Inventory on Order Cancellation | User Story | As Ops, I want reserved inventory released when an order is canceled so stock is reusable. |  | Medium | 3 |  | 0
ELI-018 | FUNC-006 | BP-1765865704672 | PH-01 | DEL-002 | EPIC-015 |  | Operations / Order Management | Inventory Management | Allocate Inventory to Orders | Reallocate Inventory After Changes | User Story | As Ops, I want inventory reallocated when orders change so fulfillment remains accurate. |  | Medium | 3 |  | 0
ELI-019 | FUNC-007 | BP-1765865704672 | PH-01 | DEL-003 | EPIC-016 |  | Sales / Account Management | Order Management | Create Sales Order | Create a Sales Order with Contract Context | User Story | As a Sales user, I want to create a sales order tied to a customer so contract pricing and rules are applied automatically. |  | Medium | 3 |  | 0
ELI-020 | FUNC-007 | BP-1765865704672 | PH-01 | DEL-003 | EPIC-016 |  | Sales / Account Management | Order Management | Create Sales Order | Validate Order Completeness Before Submission | User Story | As a Sales user, I want required order data validated so incomplete orders cannot proceed. |  | Medium | 3 |  | 0
ELI-021 | FUNC-007 | BP-1765865704672 | PH-01 | DEL-003 | EPIC-016 |  | Sales / Account Management | Order Management | Create Sales Order | Preview Pricing Before Order Submission | User Story | As a Sales user, I want to preview pricing so I can confirm totals before submitting the order. |  | Medium | 3 |  | 0
ELI-022 | FUNC-008 | BP-1765865704672 | PH-01 | DEL-003 | EPIC-017 |  | Finance / Compliance / Admin | Order Management | Evaluate Contract Pricing & Terms | Apply Tiered Pricing Automatically | User Story | As Finance, I want tiered pricing applied automatically so pricing is consistent and auditable. |  | Medium | 3 |  | 0
ELI-023 | FUNC-008 | BP-1765865704672 | PH-01 | DEL-003 | EPIC-017 |  | Finance / Compliance / Admin | Order Management | Evaluate Contract Pricing & Terms | Enforce Rebates and Penalties | User Story | As Finance, I want rebates and penalties enforced so margins and commitments are protected. |  | Medium | 3 |  | 0
ELI-024 | FUNC-008 | BP-1765865704672 | PH-01 | DEL-003 | EPIC-017 |  | Operations / Order Management | Order Management | Evaluate Contract Pricing & Terms | Recalculate Pricing on Order Changes | User Story | As Ops, I want pricing recalculated when an order changes so pricing remains accurate. |  | Medium | 3 |  | 0
ELI-025 | FUNC-009 | BP-1765865704672 | PH-01 | DEL-003 | EPIC-018 |  | Operations / Order Management | Order Management | Manage Sales Order Lifecycle | View Sales Order Status | User Story | As Ops, I want to view order status so I can track progress without manual follow-up. |  | Medium | 3 |  | 0
ELI-026 | FUNC-009 | BP-1765865704672 | PH-01 | DEL-003 | EPIC-018 |  | Operations / Order Management | Order Management | Manage Sales Order Lifecycle | Update Sales Order Status | User Story | As Ops, I want to update order status so downstream processes stay aligned. |  | Medium | 3 |  | 0
ELI-027 | FUNC-009 | BP-1765865704672 | PH-01 | DEL-003 | EPIC-018 |  | Sales / Account Management | Order Management | Manage Sales Order Lifecycle | Cancel a Sales Order | User Story | As Sales, I want to cancel an order so inventory and commitments are released correctly. |  | Medium | 3 |  | 0
ELI-028 | FUNC-010 | BP-1765865704672 | PH-01 | DEL-003 | EPIC-019 |  | Finance / Compliance / Admin | Order Management | Approve Order Exceptions & Overrides | Route Orders Requiring Approval | User Story | As Finance, I want orders that exceed thresholds routed for approval so risk is controlled. |  | Medium | 3 |  | 0
ELI-029 | FUNC-010 | BP-1765865704672 | PH-01 | DEL-003 | EPIC-019 |  | Finance / Compliance / Admin | Order Management | Approve Order Exceptions & Overrides | Approve or Reject Order Exceptions | User Story | As Finance, I want to approve or reject exceptions so decisions are explicit and traceable. |  | Medium | 3 |  | 0
ELI-030 | FUNC-010 | BP-1765865704672 | PH-01 | DEL-003 | EPIC-019 |  | Finance / Compliance / Admin | Order Management | Approve Order Exceptions & Overrides | Audit Order Approval Decisions | User Story | As Finance, I want an audit trail of approvals so reviews do not rely on email chains. |  | Medium | 3 |  | 0
ELI-031 | FUNC-011 | BP-1765865704672 | PH-01 | DEL-004 | EPIC-020 |  | Operations / Order Management | Fulfillment Orchestration | Execute Fulfillment | Assign Order to Fulfillment Resource | User Story | As Ops, I want orders assigned to the appropriate fulfillment resource so execution begins without manual routing. |  | Medium | 3 |  | 0
ELI-032 | FUNC-011 | BP-1765865704672 | PH-01 | DEL-004 | EPIC-020 |  | Warehouse & Fulfillment | Fulfillment Orchestration | Execute Fulfillment | Generate Pick Instructions | User Story | As a Warehouse user, I want system-generated pick instructions so I can fulfill orders accurately. |  | Medium | 3 |  | 0
ELI-033 | FUNC-011 | BP-1765865704672 | PH-01 | DEL-004 | EPIC-020 |  | Warehouse & Fulfillment | Fulfillment Orchestration | Execute Fulfillment | Pack and Ship Order | User Story | As a Warehouse user, I want to pack and ship orders so delivery proceeds according to service levels. |  | Medium | 3 |  | 0
ELI-034 | FUNC-012 | BP-1765865704672 | PH-01 | DEL-004 | EPIC-021 |  | Operations / Order Management | Fulfillment Orchestration | Determine Fulfillment Routing | Select Optimal Fulfillment Path | User Story | As Ops, I want the system to select the optimal fulfillment path so cost and SLA requirements are met. |  | Medium | 3 |  | 0
ELI-035 | FUNC-012 | BP-1765865704672 | PH-01 | DEL-004 | EPIC-021 |  | Operations / Order Management | Fulfillment Orchestration | Determine Fulfillment Routing | Split Orders Across Sources | User Story | As Ops, I want orders split across sources when necessary so commitments are met. |  | Medium | 3 |  | 0
ELI-036 | FUNC-012 | BP-1765865704672 | PH-01 | DEL-004 | EPIC-021 |  | Finance / Compliance / Admin | Fulfillment Orchestration | Determine Fulfillment Routing | Respect Service-Level Constraints | User Story | As Finance, I want service-level constraints enforced so contractual obligations are met. |  | Medium | 3 |  | 0
ELI-037 | FUNC-013 | BP-1765865704672 | PH-01 | DEL-004 | EPIC-022 |  | Operations / Order Management | Fulfillment Orchestration | Validate Regulated Substitutions | Propose Allowed Substitutions | User Story | As Ops, I want the system to propose allowed substitutions so I don’t manually assess eligibility. |  | Medium | 3 |  | 0
ELI-038 | FUNC-013 | BP-1765865704672 | PH-01 | DEL-004 | EPIC-022 |  | Finance / Compliance / Admin | Fulfillment Orchestration | Validate Regulated Substitutions | Validate Vendor Certifications | User Story | As Compliance, I want vendor certifications validated so non-compliant substitutions are blocked. |  | Medium | 3 |  | 0
ELI-039 | FUNC-013 | BP-1765865704672 | PH-01 | DEL-004 | EPIC-022 |  | Finance / Compliance / Admin | Fulfillment Orchestration | Validate Regulated Substitutions | Enforce Geographic and Regulatory Constraints | User Story | As Compliance, I want geographic and regulatory rules enforced so orders comply with applicable laws. |  | Medium | 3 |  | 0
ELI-040 | FUNC-014 | BP-1765865704672 | PH-01 | DEL-005 | EPIC-023 |  | Operations / Order Management | Purchase Management | Create Purchase Order | Generate Purchase Order from Demand | User Story | As Ops, I want to generate a purchase order from unmet demand so supply gaps are addressed quickly. |  | Medium | 3 |  | 0
ELI-041 | FUNC-014 | BP-1765865704672 | PH-01 | DEL-005 | EPIC-023 |  | Finance / Compliance / Admin | Purchase Management | Create Purchase Order | Select Approved Vendor for Purchase | User Story | As Finance, I want only approved vendors selectable so compliance and pricing terms are enforced. |  | Medium | 3 |  | 0
ELI-042 | FUNC-014 | BP-1765865704672 | PH-01 | DEL-005 | EPIC-023 |  | Finance / Compliance / Admin | Purchase Management | Create Purchase Order | Apply Contract Terms to Purchase Orders | User Story | As Finance, I want vendor contract terms applied so purchasing aligns with negotiated pricing and penalties. |  | Medium | 3 |  | 0
ELI-043 | FUNC-015 | BP-1765865704672 | PH-01 | DEL-005 | EPIC-024 |  | Warehouse & Fulfillment | Purchase Management | Receive Purchase Order | Receive Goods Against Purchase Order | User Story | As a Warehouse user, I want to receive goods against a PO so inventory updates accurately. |  | Medium | 3 |  | 0
ELI-044 | FUNC-015 | BP-1765865704672 | PH-01 | DEL-005 | EPIC-024 |  | Warehouse & Fulfillment | Purchase Management | Receive Purchase Order | Handle Partial or Over-Receipt | User Story | As a Warehouse user, I want to record partial or over-receipt so discrepancies are tracked. |  | Medium | 3 |  | 0
ELI-045 | FUNC-015 | BP-1765865704672 | PH-01 | DEL-005 | EPIC-024 |  | Operations / Order Management | Purchase Management | Receive Purchase Order | Close Purchase Order After Receipt | User Story | As Ops, I want POs closed after receipt so purchasing status remains accurate. |  | Medium | 3 |  | 0
ELI-046 | FUNC-016 | BP-1765865704672 | PH-01 | DEL-005 | EPIC-025 |  | Finance / Compliance / Admin | Purchase Management | Source Supply from Vendors | Evaluate Vendor Eligibility | User Story | As Compliance, I want vendor eligibility evaluated so sourcing complies with certifications and risk policies. |  | Medium | 3 |  | 0
ELI-047 | FUNC-016 | BP-1765865704672 | PH-01 | DEL-005 | EPIC-025 |  | Operations / Order Management | Purchase Management | Source Supply from Vendors | Compare Vendor Lead Times and SLAs | User Story | As Ops, I want to compare vendor lead times and SLAs so sourcing decisions meet fulfillment needs. |  | Medium | 3 |  | 0
ELI-048 | FUNC-016 | BP-1765865704672 | PH-01 | DEL-005 | EPIC-025 |  | Operations / Order Management | Purchase Management | Source Supply from Vendors | Select Optimal Vendor Source | User Story | As Ops, I want the system to select the optimal vendor so cost, compliance, and delivery goals are balanced. |  | Medium | 3 |  | 0
ELI-049 | CAP-006 | BP-1765865704672 | PH-01 | DEL-006 | EPIC-001 |  | N/A | Sales Order Processing | Sales Order Processing | Create Order Draft | Step | Capture order header and lines tied to a customer context. |  | Medium | 5 |  | 0
ELI-050 | CAP-006 | BP-1765865704672 | PH-01 | DEL-006 | EPIC-001 |  | N/A | Sales Order Processing | Sales Order Processing | Apply Contract Context | Step | Resolve active contract(s) and customer compliance requirements for this order. |  | High | 8 |  | 0
ELI-051 | CAP-006 | BP-1765865704672 | PH-01 | DEL-006 | EPIC-001 |  | N/A | Sales Order Processing | Sales Order Processing | Price and Validate Terms | Step | Apply tiered pricing, rebates/penalties, and ensure terms are consistent and auditable. |  | High | 8 |  | 0
ELI-052 | CAP-006 | BP-1765865704672 | PH-01 | DEL-006 | EPIC-001 |  | N/A | Sales Order Processing | Sales Order Processing | Route for Approval When Needed | Step | Identify orders requiring approval and route to Finance/Admin for decision. |  | Medium | 5 |  | 0
ELI-053 | CAP-006 | BP-1765865704672 | PH-01 | DEL-006 | EPIC-001 |  | N/A | Sales Order Processing | Sales Order Processing | Release Order to Fulfillment | Step | Transition approved orders to a fulfillment-ready state and emit downstream signals. |  | Medium | 5 |  | 0
ELI-054 | CAP-007 | BP-1765865704672 | PH-01 | DEL-007 | EPIC-002 |  | N/A | Fulfillment Execution | Fulfillment Execution | Determine Routing and Splits | Step | Choose warehouse/vendor sources and split the order when needed to meet SLAs and rules. |  | High | 8 |  | 0
ELI-055 | CAP-007 | BP-1765865704672 | PH-01 | DEL-007 | EPIC-002 |  | N/A | Fulfillment Execution | Fulfillment Execution | Allocate Inventory | Step | Reserve inventory for the chosen sources and prevent double-allocation. |  | High | 8 |  | 0
ELI-056 | CAP-007 | BP-1765865704672 | PH-01 | DEL-007 | EPIC-002 |  | N/A | Fulfillment Execution | Fulfillment Execution | Validate Substitutions and Compliance | Step | Validate substitutions against contracts, certifications, and geographic/regulatory constraints. |  | High | 8 |  | 0
ELI-057 | CAP-007 | BP-1765865704672 | PH-01 | DEL-007 | EPIC-002 |  | N/A | Fulfillment Execution | Fulfillment Execution | Generate Pick/Pack/Ship Instructions | Step | Produce actionable fulfillment instructions for warehouse execution. |  | Medium | 5 |  | 0
ELI-058 | CAP-007 | BP-1765865704672 | PH-01 | DEL-007 | EPIC-002 |  | N/A | Fulfillment Execution | Fulfillment Execution | Confirm Shipment and Update Status | Step | Mark shipments dispatched, attach tracking, and update order lifecycle state. |  | Medium | 5 |  | 0
ELI-059 | CAP-008 | BP-1765865704672 | PH-01 | DEL-008 | EPIC-003 |  | N/A | Purchase Replenishment | Purchase Replenishment | Detect Supply Gap | Step | Identify when demand exceeds available inventory and triggers purchasing. |  | Medium | 5 |  | 0
ELI-060 | CAP-008 | BP-1765865704672 | PH-01 | DEL-008 | EPIC-003 |  | N/A | Purchase Replenishment | Purchase Replenishment | Select Eligible Vendor | Step | Ensure vendor eligibility and select optimal vendor based on lead times and rules. |  | Medium | 5 |  | 0
ELI-061 | CAP-008 | BP-1765865704672 | PH-01 | DEL-008 | EPIC-003 |  | N/A | Purchase Replenishment | Purchase Replenishment | Create Purchase Order | Step | Create PO with applied vendor contract terms and required delivery dates. |  | Medium | 5 |  | 0
ELI-062 | FUNC-031 | BP-1765865704672 | PH-01 | DEL-010 | EPIC-026 |  | N/A | Inventory / WMS Service | Inventory / WMS Service | Inventory / WMS Service | System | Source of truth for on-hand/available inventory and the execution surface for reservations and receiving updates. |  | High | 8 |  | 0
ELI-063 | FUNC-032 | BP-1765865704672 | PH-01 | DEL-011 | EPIC-027 |  | N/A | Vendor Portal / Supplier API | Vendor Portal / Supplier API | Vendor Portal / Supplier API | System | External vendor system(s) providing item availability, lead times, SLAs, and certification status for sourcing and substitution decisions. |  | High | 8 |  | 0
ELI-064 | FUNC-033 | BP-1765865704672 | PH-01 | DEL-012 | EPIC-028 |  | N/A | Compliance Rules & Restrictions Service | Compliance Rules & Restrictions Service | Compliance Rules & Restrictions Service | System | External or internal service that returns compliance rules, geo restrictions, and item-level regulatory attributes for evaluation at order and substitution time. |  | High | 8 |  | 0
ELI-065 | FUNC-034 | BP-1765865704672 | PH-01 | DEL-013 | EPIC-029 |  | N/A | Messaging / Event Bus | Messaging / Event Bus | Messaging / Event Bus | System | Central eventing platform used to publish OMS domain events for consumers (ERP integration workers, dashboards, notifications). |  | Medium | 5 |  | 0
ELI-066 | CAP-014 | BP-1765865704672 | PH-01 | DEL-009 | EPIC-004 |  | N/A | Foundations | Navigation and Component Library | Component Library | Subsystem | Choose and install a design system |  | Medium | 5 |  | 0
ELI-067 | CAP-014 | BP-1765865704672 | PH-01 | DEL-009 | EPIC-004 |  | N/A | Foundations | Navigation and Component Library | Global Layout Templates | Subsystem | Define dashboard shell, sidebar, headers, and modal containers. |  | Medium | 5 |  | 0
ELI-068 | CAP-014 | BP-1765865704672 | PH-01 | DEL-009 | EPIC-004 |  | N/A | Foundations | Navigation and Component Library | Navigation Structure | Subsystem | Set up route configuration and page access logic |  | Medium | 5 |  | 0
ELI-069 | CAP-015 | BP-1765865704672 | PH-01 | DEL-009 | EPIC-005 |  | N/A | Foundations | User Management | User Schema | Subsystem | Define core fields like name, email, auth method, and settings. |  | Medium | 5 |  | 0
ELI-070 | CAP-015 | BP-1765865704672 | PH-01 | DEL-009 | EPIC-005 |  | N/A | Foundations | User Management | Profile Management | Subsystem | Allow users to update their information, timezone, and avatar. |  | Low | 3 |  | 0
ELI-071 | CAP-015 | BP-1765865704672 | PH-01 | DEL-009 | EPIC-005 |  | N/A | Foundations | User Management | Session Tracking | Subsystem | Log login history, session duration, and access activity. |  | Medium | 5 |  | 0
ELI-072 | CAP-016 | BP-1765865704672 | PH-01 | DEL-009 | EPIC-006 |  | N/A | Foundations | Authentication & Security | Auth System | Subsystem | Integrate platforms like Auth0, Clerk, or Firebase Auth. |  | Medium | 5 |  | 0
ELI-073 | CAP-016 | BP-1765865704672 | PH-01 | DEL-009 | EPIC-006 |  | N/A | Foundations | Authentication & Security | API Protection | Subsystem | Use JWTs or sessions to authorize requests on protected endpoints. |  | High | 8 |  | 0
ELI-074 | CAP-016 | BP-1765865704672 | PH-01 | DEL-009 | EPIC-006 |  | N/A | Foundations | Authentication & Security | Encryption | Subsystem | Encrypt sensitive data both in transit (HTTPS) and at rest (AES). |  | High | 8 |  | 0
ELI-075 | CAP-017 | BP-1765865704672 | PH-01 | DEL-009 | EPIC-007 |  | N/A | Foundations | Data Management | Object Schema Design | Subsystem | Model core data object of the system |  | High | 8 |  | 0
ELI-076 | CAP-017 | BP-1765865704672 | PH-01 | DEL-009 | EPIC-007 |  | N/A | Foundations | Data Management | CRUD APIs | Subsystem | Expose backend endpoints for accessing and modifying |  | Medium | 5 |  | 0
ELI-077 | CAP-017 | BP-1765865704672 | PH-01 | DEL-009 | EPIC-007 |  | N/A | Foundations | Data Management | Audit Logging | Subsystem | Capture a change log for critical actions like edits, deletions, or merges. |  | High | 8 |  | 0
ELI-078 | CAP-018 | BP-1765865704672 | PH-01 | DEL-009 | EPIC-008 |  | N/A | Foundations | Backend Infrastructure | API Gateway & Routing | Subsystem | Centralize request routing, versioning, throttling, and request/response transformations for REST/GraphQL. |  | Medium | 5 |  | 0
ELI-079 | CAP-018 | BP-1765865704672 | PH-01 | DEL-009 | EPIC-008 |  | N/A | Foundations | Backend Infrastructure | Message & Task Queue | Subsystem | Support async jobs, scheduled work, and event-driven workflows (e.g., retries, dead-letter queues). |  | High | 8 |  | 0
ELI-080 | CAP-018 | BP-1765865704672 | PH-01 | DEL-009 | EPIC-008 |  | N/A | Foundations | Backend Infrastructure | Observability | Subsystem | Collect logs, metrics, and traces with correlation IDs and alerting thresholds. |  | Medium | 5 |  | 0
ELI-081 | CAP-019 | BP-1765865704672 | PH-01 | DEL-009 | EPIC-009 |  | N/A | Foundations | DevOps | Environment Configuration | Subsystem | Use .env files and secrets management for tokens, keys, and DB strings. |  | Medium | 5 |  | 0
ELI-082 | CAP-019 | BP-1765865704672 | PH-01 | DEL-009 | EPIC-009 |  | N/A | Foundations | DevOps | CI/CD | Subsystem | Deploy with GitHub Actions, Vercel, or custom workflows for build/test/release. |  | Medium | 5 |  | 0
ELI-083 | CAP-019 | BP-1765865704672 | PH-01 | DEL-009 | EPIC-009 |  | N/A | Foundations | DevOps | Automated Testing | Subsystem | Integrate unit, integration, and end-to-end test pipelines. |  | Medium | 5 |  | 0

## Phase # - Resource Plan
[Solution] Resource Plan
|  | Stage |  | Validate | Develop | Develop | Develop | Develop | Develop | Develop | Develop | Enable | Enable
Nymbl Resource | Total Hours | Total Amount | Rate | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8
Strategy Partner | 30 | 8250 | 275 | 5 | 5 | 5 | 5 | 5 | 5
Technology Partner | 120 | 31200 | 260 | 20 | 20 | 20 | 20 | 20 | 20
Solution Architect | 480 | 110400 | 230 | 80 | 80 | 80 | 80 | 80 | 80
Product Designer | 160 | 32000 | 200 | 80 | 80
Project Manager | 0 | 0 | 190
Lead Developer | 480 | 86400 | 180 |  | 120 | 120 | 120 | 120
Developer | 0 | 0 | 175
Developer | 0 | 0 | 175
AI Engineer | 0 | 0 | 220
Support Engineer | 0 | 0 | 190
Cloud Architect | 50 | 12000 | 240 |  |  |  |  | 40 | 10
Quality Assurance Manager | 0 | 0 | 130
Documentation Lead | 0 | 0 | 150
Total Hours | 1320 |  |  | 185 | 305 | 225 | 225 | 265 | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total USD Amount |  | 280250 |  | 40975 | 62575 | 46575 | 46575 | 56175 | 27375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Quarter Totals |  |  | 40975 | 155725 |  |  | 83550 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 10% Contigency
| Yearly Totals |  |  | 196700 |  |  |  | 83550 | [11 empty] | 0
Role Stats
| Average Rate |  | 201.1538
| AVG FTE |  |  | 1.0278 | 1.6944 | 1.25 | 1.25 | 1.4722 | 0.63889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[Client] Time Investment
| Year |  |  | 2025 |  |  |  | 2026 | [11 empty] | 2027
| Stage |  |  | Validate | Build |  |  | Enable | Plan | Validate | Build |  |  |  | Enable | Plan | Validate | Build |  |  | Enable | Plan | Validate | Build |  |  | Enable
| Quarter |  |  | Q3 | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
A&M Resource | Total Hours |  |  | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December
Stakeholder | 0
Product Owner | 0
Subject Matter Experts | 0
-- Case Management | 0
-- Reporting and Filing | 0
Beta Users | 0
Total Hours | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Quarter Totals |  |  | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| Yearly Totals |  |  | 0 |  |  |  | 0 | [11 empty] | 0

## Effort Guide
Fibonacci Sequence Definition
Scale | Description
1 | (Trivial):** Tiny tweak (e.g. typo or label change), virtually no uncertainty.
2 | (Very Small): Simple story with clear criteria (e.g. add a field), minimal design.
3 | (Small): Low‑risk work touching a few components (e.g. new API endpoint).
5 | (Medium): Self‑contained feature in one sprint (e.g. profile editing).
8 | (Medium–Large): Multi‑scenario story (e.g. onboarding wizard), more testing.
13 | (Large/Epic Boundary): Epic‑sized but sprint‑length with risk (e.g. checkout flow).
20 | (Very Large Epic): Multi‑sprint initiative needing breakdown (e.g. billing migration).
40 | (Huge Initiative): Major multi‑sprint program with dependencies.
100 | (Monolithic): Placeholder for anything too big—must be decomposed further.

## ROI
| Year 1 | Year 2 | Year 3 |  |  | Year 1 | Year 2 | Year 3
Order Per Rep | 10 | 15 | 20 |  | Order Per Rep | 10 | 11 | 12
Orders | 300 | 675 | 1300 |  | Orders | 300 | 385 | 480
$ per Order | 20000 | 21000 | 22000 |  | $ per Order | 20000 | 21000 | 22000
Total $ | 6000000 | 14175000 | 28600000 |  | Total $ | 6000000 | 8085000 | 10560000
Gross Profit % | 0.2 | 0.21 | 0.22 |  | Gross Profit % | 0.2 | 0.21 | 0.22
Total Gross | 1200000 | 2976750 | 6292000 |  | Total Gross | 1200000 | 1697850 | 2323200
Sales Reps | 30 | 45 | 65 |  | Sales Reps | 30 | 35 | 40
Sales Rep Commision | 120000 | 297675 | 629200 |  | Sales Rep Commision | 120000 | 169785 | 232320
Operation HC | 1800000 | 1980000 | 2178000 |  | Operation HC | 1800000 | 1980000 | 2178000
OMS Cost | 300000 | 100000 | 10000 |  | OMS Cost
Net Profit w OMS | -1020000 | 599075 | 3474800 |  | Net Profit w/o OMS | -720000 | -451935 | -87120
| Year 1 | Year 2 | Year 3 | 3 Year Total
Net Profit w OMS | -1020000 | 599075 | 3474800 | 3053875
Net Profit w/o OMS | -720000 | -451935 | -87120 | -1259055
| -300000 | 1051010 | 3561920 | 4312930