## DEL-Deliverables
deliverable_id | strategy_ref | blueprint_ref | phase_ref | requirement_type | deliverable_name | deliverable_description | notes | complexity | effort | hours | Epic Roll Up | ELI Roll Up
DEL-001 | CAP-002 | BLUE-SDMP-01 | PH-01 | Experience | Project Management | Scope, plan, track, and deliver projects with milestone-driven execution. |  | Medium | 13 |  | 4 | 16
DEL-002 | CAP-003 | BLUE-SDMP-01 | PH-01 | Experience | Time Management | Capture and review time entries for accurate billing and productivity insights. |  | Low | 5 |  | 1 | 4
DEL-003 | CAP-016 | BLUE-SDMP-01 | PH-01 | Workflow | Kickoff → Invoice Value Stream | Links project execution to invoicing through milestone validation and financial tracking. |  | Medium | 8 |  | 1 | 5
DEL-004 | FOUNDATIONS | BLUE-SDMP-01 | PH-01 | Foundation | Foundations | Infrastructure and foundational systems |  |  |  |  | 7 | 7

## EPIC - Epics
epic_id | strategy_ref | blueprint_ref | phase_ref | deliverable_id | deliverable_name | epic_type | epic_name | epic_user_story | notes | complexity | effort | hours | ELI Roll Up
EPIC-001 | CAP-016 | BLUE-SDMP-01 | PH-01 | DEL-003 | Kickoff → Invoice Value Stream | Workflow | Kickoff → Invoice Value Stream | Links project execution to invoicing through milestone validation and financial tracking. |  | Medium | 8 |  | 5
EPIC-002 | CAP-021 | BLUE-SDMP-01 | PH-01 | DEL-004 | Foundations | Foundation | Navigation & Component Library | Reusable front-end foundation for consistent UX and efficient development. |  | Low | 5 |  | 1
EPIC-003 | CAP-022 | BLUE-SDMP-01 | PH-01 | DEL-004 | Foundations | Foundation | User Management | Manage identities, profiles, sessions, and multi-account access. |  | Low | 5 |  | 1
EPIC-004 | CAP-023 | BLUE-SDMP-01 | PH-01 | DEL-004 | Foundations | Foundation | Authentication & Security | Secure authentication, authorization, and encryption. |  | Low | 5 |  | 1
EPIC-005 | CAP-024 | BLUE-SDMP-01 | PH-01 | DEL-004 | Foundations | Foundation | Data Management | Govern and synchronize business, project, and financial data. |  | Low | 5 |  | 1
EPIC-006 | CAP-025 | BLUE-SDMP-01 | PH-01 | DEL-004 | Foundations | Foundation | Backend Infrastructure | Runtime, API, orchestration, and observability backbone. |  | Medium | 8 |  | 1
EPIC-007 | CAP-026 | BLUE-SDMP-01 | PH-01 | DEL-004 | Foundations | Foundation | AI Infrastructure | Operate AI features safely and efficiently. |  | Medium | 8 |  | 1
EPIC-008 | CAP-027 | BLUE-SDMP-01 | PH-01 | DEL-004 | Foundations | Foundation | DevOps Infrastructure | CI/CD and environment management. |  | Low | 5 |  | 1
EPIC-009 | FUNC-010 | BLUE-SDMP-01 | PH-01 | DEL-001 | Project Management | Use Case | Manage Projects | Track status, risks, and schedule adjustments. |  | Medium | 5 |  | 4
EPIC-010 | FUNC-011 | BLUE-SDMP-01 | PH-01 | DEL-001 | Project Management | Use Case | Manage Tasks | Create, assign, and track tasks within projects. |  | Medium | 5 |  | 4
EPIC-011 | FUNC-014 | BLUE-SDMP-01 | PH-01 | DEL-001 | Project Management | Use Case | Manage Milestones | Define and track milestones and billing gates. |  | Medium | 5 |  | 4
EPIC-012 | FUNC-016 | BLUE-SDMP-01 | PH-01 | DEL-001 | Project Management | Use Case | Update Guidance | Provide contextual help and best practices at each step. |  | Low | 3 |  | 4
EPIC-013 | FUNC-019 | BLUE-SDMP-01 | PH-01 | DEL-002 | Time Management | Use Case | Track Project Time Entries | Aggregate time at the project level for reporting. |  | Low | 3 |  | 4